## AN
Akcijski načrt IUMV 2021-2027
Vsi projekti | Šifra | Sklad / Posebni cilj / Vrsta ukrepa / Ukrep | Kategorija |  | Nosilec vsebine | Način dodelitve | EU - stanje verzije IUMV - marec 2025 | RAZLIKA NOVI AN-STARA (EU zneski) | Celoten znesek | EU prispevek | SLO udeležba | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Kontrola | Opomba | Proračun 2026 | 2027 | Razlika 2026 | EU | SLO
| Skupaj: | [7 empty] | 145754028.9291 | 124900295.7091 | 20853733.22 | 0 | 861539.5637 | 4581460.6286 | 10332248.91 | 20862243.12 | 44596832.5691 | 17744995.17 | 22888839.7 | -0.0023
| B.SO1 | Evropsko integrirano upravljanje meja | Posebni cilj |  |  |  | #REF! | #REF! | 116217534.18 | 99605467.65 | 16612066.53 | 0 | 19428.45 | 1993464.68 | 6176836.91 | 15692495.78 | 36419821.84 | 13719995.17 | 18309622.08 | -1.4552e-11
| B.SO1.1 | Ukrepi, zajeti s členom 12(1) (75%) | Vrsta ukrepa |  |  |  | 31312100.01 | 10924419.45 | 56315359.34 | 42236519.46 | 14078839.88 | 0 | 19428.45 | 391753.5 | 2931217.31 | 4215060.9 | 21219768.29 | 825666.24 | 2826595.38 | 1.0186e-10
| B.SO1.1.1 | Mejne kontrole | Ukrep |  |  |  | 838070.01 | 19267.5 | 1143116.68 | 857337.51 | 285779.17 | 0 | 0 | 0 | 168000 | 604317.8 | 370798.88 | 0 | 0 | 0
1 | B.SO1.1.1-01 | Zamenjava informacijske opreme na meji | Projekt | Replacement of IT equipment at the border | Policija - UIT | N | 106732.5 | 19267.5 | 168000 | 126000 | 42000 |  | 0 | 0 | 168000 | 0 | 0 | 0 | 0 | 0
2 | B.SO1.1.1-02 | PKI infrastruktura - pasivna avtentikacija, terminalska aplikacija | Projekt | PKI infrastructure - passive authentication, terminal application | Policija - UIT | N | 635037.51 | 0 | 846716.68 | 635037.51 | 211679.17 |  | 0 | 0 | 0 | 604317.8 | 242398.88 | 0 | 0 | 0
3 | B.SO1.1.1-03 | Naprave za preverjanje pristnosti dokumentov | Projekt | Document authentication devices | Policija - UUP | N | 96300 | 0 | 128400 | 96300 | 32100 |  | 0 | 0 | 0 | 0 | 128400 | 0 | 0 | 0
| B.SO1.1.3 | Varovanje meje - kopenska oprema | Ukrep |  |  |  | 2675000 | 0 | 3566666.68 | 2675000 | 891666.68 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 2566666.68 | 0
4 | B.SO1.1.3-01 | Nabava ročnih in mobilnih termovizij | Projekt | Purchasing handheld and mobile thermal imaging equipment | Policija - UUP | N | 535000 | 0 | 713333.34 | 535000 | 178333.34 |  | 0 | 0 | 0 | 0 | 0 | 0 | 713333.34 | 0
5 | B.SO1.1.3-02 | Nabava prevoznih sredstev | Projekt | Purchase of means of transport | Policija - UUP | N | 2140000 | 0 | 2853333.34 | 2140000 | 713333.34 |  | 0 | 0 | 1000000 | 0 | 0 | 0 | 1853333.34 | 0
| B.SO1.1.4 | Varovanje meje - pomorska oprema | Ukrep |  |  |  | 8194000 | 3000000 | 14925333.34 | 11194000 | 3731333.34 | 0 | 0 | 0 | 0 | 0 | 14925333.34 | 0 | 0 | 0
6 | B.SO1.1.4-01 | Pomorsko plovilo za varovanje meje-čolni | Projekt | Maritime Border Guard Vessel-Boats | Policija - UUP | N | 6375000 | 3000000 | 12500000 | 9375000 | 3125000 |  | 0 | 0 | 0 | 0 | 12500000 | 0 | 0 | 0
7 | B.SO1.1.4-02 | Radarski sistem | Projekt | Radar system | Policija - UUP | N | 1819000 | 0 | 2425333.34 | 1819000 | 606333.34 |  | 0 | 0 | 0 | 0 | 2425333.34 | 0 | 0 | 0
| B.SO1.1.7 | Tehnični in operativni ukrepi na schengenskem območju, vezani na nadzor meje | Ukrep |  |  |  | 1170000 | 10371651.95 | 15388869.28 | 11541651.95 | 3847217.33 | 0 | 13960.85 | 68865.04 | 133333.33 | 554170.03 | 663142.92 | 71666.67 | 47861.17 | 0
8 | B.SO1.1.7-01 | Posodobitev aplikacij za izmenjave podatkov (EUROPOL, INTERPOL, SIRENE) | Projekt | Update of data exchange applications (EUROPOL, INTERPOL, SIRENE) | Policija - UIT | N | 722250 | 0 | 963000 | 722250 | 240750 |  | 0 | 28196.64 | 0 | 466503.36 | 468300 | 0 | 0 | 0
9 | B.SO1.1.7-02 | Sodelovanje ekspertov na schengenskih evalvacijah | Projekt | Participation of experts in Schengen evaluations | Policija - UUP | N | 100000 | 0 | 133333.34 | 100000 | 33333.34 |  | 1912.12 | 8911.64 | 83333.33 | 16000 | 23176.25 | 0 | 0 | 0
10 | B.SO1.1.7-03 | Mednarodni prostor za zavrnjene državljane tretjih držav | Projekt | International space for refused third-country nationals | Policija - PU KR | N | 267500 | 0 | 356666.67 | 267500 | 89166.67 |  | 12048.73 | 31756.76 | 50000 | 71666.67 | 71666.67 | 71666.67 | 47861.17 | 0
11 | B.SO1.1.7-04 | Zamenjava opreme na mejnih prehodih | Projekt | Replacement of equipment at border crossing points | MNZ - DLN | N | 80250 | -5250 | 100000 | 75000 | 25000 |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0
12 | B.SO1.1.7-05 | Izpolnitev schengenskih priporočil | Projekt |  | Policija - UUP | N |  |  | 4000000 | 3000000 | 1000000 |  | 0 | 0 | 0 | 100000 | 1200000 | 1300000 | 1400000 | 0
13 | B.SO1.1.7-06 | Prostori za izvajanje Uredbe o preverjanju državljanov tretjih držav na zunanjih mejah - projekt Policije 6 (75%) | Projekt | Implementation of EU rules on screening linked to the implementation of the Pact on Migration and Asylum; infrastructure (75%) | Policija - UUP | N | 15611248.331 | -8234346.381 | 9835869.27 | 7376901.95 | 2458967.32 |  | 0 | 0 | 40000 | 300000 | 1500000 | 4500000 | 3495869.27 | 0 |  | 300000 | 2769294 | 0
| B.SO1.1.9 | Analiza tveganja | Ukrep |  |  |  | 374500 | 0 | 499333.34 | 374500 | 124833.34 | 0 | 5467.6 | 127642.08 | 102000 | 108666.67 | 155556.99 | 0 | 0 | 0
14 | B.SO1.1.9-01 | Strateška podpora analizam tveganja | Projekt | Strategic support for risk analyses | Policija - UUP | N | 374500 | 0 | 499333.34 | 374500 | 124833.34 |  | 5467.6 | 127642.08 | 102000 | 108666.67 | 155556.99 | 0 | 0 | 0
| B.SO1.1.10 | Obdelava podatkov in informacij | Ukrep |  |  |  | 5053610 | 0 | 6738146.68 | 5053610 | 1684536.68 | 0 | 0 | 1396.45 | 794550.65 | 1732782.69 | 3254083.13 | 748666.24 | 206667.52 | -2.9104e-11
15 | B.SO1.1.10-01 | Prenova za interoperabilnost in stroški razvijalcev | Projekt | Redesign for interoperability and developer costs | Policija - UIT | N | 1934560 | 0 | 2579413.34 | 1934560 | 644853.34 |  | 0 | 1396.45 | 365333.34 | 752000 | 927349.79 | 326666.24 | 206667.52 | 0
16 | B.SO1.1.10-02 | Prenova nacionalnega sistema EUROSUR | Projekt | Overhaul of the EUROSUR national system | Policija - UIT | N | 2220250 | 0 | 2960333.34 | 2220250 | 740083.34 |  | 0 | 0 | 229217.31 | 717449.36 | 1781666.67 | 232000 | 0 | 0
17 | B.SO1.1.10-03 | Izboljšanje analitskig zmoglivosti za naprednejša ocenjevanja tveganj v smeri "hot spot" analiz in odkrivanja zapletenih povezav v podatkih. | Projekt | Improving analytical capabilities for more advanced risk assessments towards "hot spot" analyses and discovering complex links in data. | Policija - UIT | N | 577800 | 0 | 770400 | 577800 | 192600 |  | 0 | 0 | 0 | 200000 | 380400 | 190000 | 0 | 0
18 | B.SO1.1.10-04 | Vzpostavitev NCC | Projekt | Establishing the NCC | Policija - UUP | N | 321000 | 0 | 428000 | 321000 | 107000 |  | 0 | 0 | 200000 | 63333.33 | 164666.67 | 0 | 0 | -2.9104e-11 |  | 85333 |  | 21999.67 | 16499.7525 | 5499.9175
| B.SO1.1.20 | Obsežni informacijski sistemi - EES | Ukrep |  |  |  | 1192515 | 1912500 | 4140020 | 3105015 | 1035005 | 0 | 0 | 182306.97 | 533333.33 | 333333.33 | 541046.37 | 0 | 0 | 1.1642e-10
19 | B.SO1.1.20-01 | Razvoj, nadgranje in IT oprema EES |  | EES development, upgrading and IT equipment | Policija - UIT | N | 1192515 | 0 | 1590020 | 1192515 | 397505 |  | 0 | 182306.97 | 533333.33 | 333333.33 | 541046.37 | 0 | 0 | 1.1642e-10 |  | 300000 |  | -33333.33 | -24999.9975 | -8333.3325
20 | B.SO1.1.20-02 | Nakup čitalcev za upravne enote | Projekt |  | Ministrstvo za digitalno preobrazbo | N |  |  | 2550000 | 1912500 | 637500 |  | 0 | 0 | 0 | 2550000 | 0 | 0 | 0 | 0
| B.SO1.1.21 | Obsežni informacijski sistemi - ETIAS | Ukrep |  |  |  | 1007405 | 0 | 1343206.67 | 1007405 | 335801.67 | 0 | 0 | 0 | 200000 | 412000 | 720473.33 | 5333.33 | 5400.01 | 0
21 | B.SO1.1.21-01 | ETIAS | Projekt | ETIAS | Policija - UIT | N | 991355 | 0 | 1321806.67 | 991355 | 330451.67 |  | 0 | 0 | 200000 | 406666.67 | 715140 | 0 | 0 | 0
22 | B.SO1.1.21-02 | ETIAS usposabljanje, študijski obiski, delovni sestanki | Projekt | ETIAS training, study visits, working meetings | Policija - UKP | N | 16050 | 0 | 21400 | 16050 | 5350 |  | 0 | 0 | 0 | 5333.33 | 5333.33 | 5333.33 | 5400.01 | 0
| B.SO1.1.24 | Obsežni informacijski sistemi - SIS | Ukrep |  |  |  | 321000 | 0 | 428000 | 321000 | 107000 | 0 | 0 | 11542.96 | 0 | 416457.04 | 0 | 0 | 0 | 0
23 | B.SO1.1.24-01 | Nadgradnja SIS | Projekt | SIS upgrade | Policija - UIT | N | 321000 | 0 | 428000 | 321000 | 107000 |  | 0 | 11542.96 | 0 | 416457.04 | 0 | 0 | 0 | 0
| B.SO1.1.25 | Obsežni informacijski sistemi - SIS | Ukrep |  |  |  | 10700000 | -4700000 | 8000000 | 6000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0
24 | B.SO1.1.25-01 | Zmanjšanje izpostavljenosti ITSP pred kibernetskimi tveganji in grožnjami (75%) |  | Reducing ITSP exposure to cyber risks and threats | Policija - UIT | N | 10700000 | -5075000 | 7500000 | 5625000 | 1875000 |  | 0 | 0 | 0 | 0 | 2500000 | 2500000 | 2500000 | 0 |  | 1244438.33 |  | 1244438.33 | 1137431.33 | 107007
25 | B.SO1.1.25-02 | Vzpostavitev in prilagoditev za varnost pomembnih IT sistemov |  |  | Policija - UIT | N | 10700000 | -10325000 | 500000 | 375000 | 125000 |  | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0
| B.SO1.1.29 | Obsežni informacijski sistemi - interoperabilnost | Ukrep |  |  |  | 107000 | 0 | 142666.67 | 107000 | 35666.67 | 0 | 0 | 0 | 0 | 53333.34 | 89333.33 | 0 | 0 | 1.4552e-11
26 | B.SO1.1.29-01 | Varovanje osebnih podatkov za interoperabilnost | Projekt | Protecting personal data for interoperability | Policija - UIT | N | 107000 | 0 | 142666.67 | 107000 | 35666.67 |  | 0 | 0 | 0 | 53333.34 | 89333.33 | 0 | 0 | 1.4552e-11
| B.SO1.2 | Posebni ukrepi (75%) | Vrsta ukrepa |  |  |  | #REF! | #REF! | 10607155.14 | 9546439.62 | 1060715.52 | 0 | 0 | 0 | 0 | 2000000 | 3000000 | 1000000 | 4607155.14 | 0
| B.SO1.2.7 | Tehnični in operativni ukrepi na schengenskem območju, vezani na nadzor meje | Ukrep |  |  |  | 106732.5 | 1693267.5 | 2000000 | 1800000 | 200000 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0
27 | B.SO1.2.7-01 | Nakup prevoznih sredstev za izvajanje postopkov, povezanih s preverjanjem (90%) | Projekt |  | Policija - UUP | N | 106732.5 | 1693267.5 | 2000000 | 1800000 | 200000 |  | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 |  |  |  | 0
| B.SO1.2.19 | Obsežni informacijski sistemi - EURODAC za namene upravljanja meja | Ukrep |  |  |  | #REF! | #REF! | 8607155.14 | 7746439.62 | 860715.52 | 0 | 0 | 0 | 0 | 2000000 | 1000000 | 1000000 | 4607155.14 | 0
28 | B.SO1.2.19-01 | Impementacija EURODAC RECAST (90%) | Projekt |  | Policija - UIT | N | 535000 | 7211439.62 | 8607155.14 | 7746439.62 | 860715.52 |  | 0 | 0 | 0 | 2000000 | 1000000 | 1000000 | 4607155.14 | 0 |  | 2360000 |  | 360000 | 324000 | 36000
| B.SO1.3 | Ukrepi iz priloge IV (90%) | Vrsta ukrepa |  |  |  | 9395000 | 3857600 | 14725111.13 | 13252600 | 1472511.13 | 0 | 0 | 64021.87 | 1115911.12 | 2286222.88 | 3853402.45 | 3826365.53 | 3579187.28 | -1.1642e-10
| B.SO1.3.3 | Varovanje meje - kopenska oprema | Ukrep |  |  |  | 856000 | 0 | 951111.12 | 856000 | 95111.12 | 0 | 0 | 0 | 111111.12 | 333333.33 | 168888.89 | 168888.89 | 168888.89 | 0
29 | B.SO1.3.3-01 | Nabava ročnih in mobilnih termovizij in prevoznih sredstev | Projekt | Procurement of handheld and mobile thermal imaging equipment and vehicles | Policija - SGDP | N | 856000 | 0 | 951111.12 | 856000 | 95111.12 |  | 0 | 0 | 111111.12 | 333333.33 | 168888.89 | 168888.89 | 168888.89 | 0
| B.SO1.3.18 | Skupna napotitev uradnikov za zvezo in priseljevanje | Ukrep |  |  |  | 4601000 | 0 | 5112222.23 | 4601000 | 511222.23 | 0 | 0 | 33503.8 | 200000 | 555555.55 | 1437913.41 | 1437913.42 | 1447336.05 | 0
30 | B.SO1.3.18-01 | Uradniki za zvezo za priseljevanje | Projekt | Immigration liaison officers | Policija - SGDP | N | 2354000 | 0 | 2615555.56 | 2354000 | 261555.56 |  | 0 | 33503.8 | 100000 | 333333.33 | 713098.6 | 713098.6 | 722521.23 | 0
31 | B.SO1.3.18-02 | Napotitve policistov, ki nudijo pomoč pri varovanju zunanje schengenske meje (Severna Makedonija, Srbija) | Projekt | Deployment of police officers to assist in the protection of the external Schengen border (North Macedonia, Serbia) | Policija - SGDP | N | 2247000 | 0 | 2496666.67 | 2247000 | 249666.67 |  | 0 | 0 | 100000 | 222222.22 | 724814.81 | 724814.82 | 724814.82 | 0
| B.SO1.3.25 | Obsežni informacijski sistemi - interoperabilnost | Ukrep |  |  |  | 3938000 | 3857600 | 8661777.78 | 7795600 | 866177.78 | 0 | 0 | 30518.07 | 804800 | 1397334 | 2246600.15 | 2219563.22 | 1962962.34 | -1.1642e-10
32 | B.SO1.3.25-01 | Razvoj in nacionalna implementacija EU projektov v sklopu interoperabilnosti | Projekt | Development and national implementation of EU interoperability projects | Policija - UIT | N | 3938000 | 2787600 | 7472888.89 | 6725600 | 747288.89 |  | 0 | 30518.07 | 804800 | 864000 | 1847646.15 | 1962962.33 | 1962962.34 | 0
33 | B.SO1.3.25-02 | Izvedba nacionalnega MID orodja (Priloga IV, 90%) |  | Implementation of the national MID tool (Annex IV, 90%) | Policija - UIT | N | 1070000 | 0 | 1188888.89 | 1070000 | 118888.89 |  | 0 | 0 | 0 | 533334 | 398954 | 256600.89 | 0 | -1.1642e-10
| B.SO1.4 | Operativna podpora (100%) | Vrsta ukrepa |  |  |  | #REF! | #REF! | 33525321.07 | 33525321.07 | 0 | 0 | 0 | 1537689.31 | 2129708.48 | 6943962 | 8065113.4 | 7805963.4 | 7042884.48 | 0
| B.SO1.4.26 | Operativna podpora za integrirano upravljanje meja | Ukrep |  |  |  | 14039728.16 | 18950592.91 | 32990321.07 | 32990321.07 | 0 | 0 | 0 | 1537689.31 | 2029708.48 | 6843962 | 7730113.4 | 7805963.4 | 7042884.48 | 0
34 | B.SO1.4.26-01 | Vzdrževanje aplikacij | Projekt | Update of data exchange applications (EUROPOL, INTERPOL, SIRENE) | Policija - UIT | N | 214000 | 100000 | 314000 | 314000 | 0 |  | 0 | 0 | 0 | 0 | 98000 | 147000 | 69000 | 0
35 | B.SO1.4.26-02 | Vzdrževanje SIS II komunikacijskega vmesnika (SIB) (100%)-OP | Projekt | Maintenance of SIS II Communication Interface (SIB) (100%)-OP | Policija - UIT | N | 771778.16 | 0 | 771778.16 | 771778.16 | 0 |  | 0 | 86964 | 103962 | 103962 | 158963.4 | 158963.4 | 158963.36 | 0
36 | B.SO1.4.26-03 | Vzdrževanje pomorskega radarskega sistema | Projekt | Maintenance of the maritime radar system | Policija - UIT | N | 470800 | 0 | 470800 | 470800 | 0 |  | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 70800 | 0
37 | B.SO1.4.26-05 | Usposabljanje za nadzor zunanje schengenske meje dodatna specialistična usposabljanja - 5.000€ letno (namestitev in prehrana), skupaj 35.000€ | Projekt | Training for external Schengen border control additional specialised training - €5,000 per year (accommodation and meals), total €35,000 | Policija - PA | N | 37450 | 0 | 37450 | 37450 | 0 |  | 0 | 0 | 0 | 20000 | 17450 | 0 | 0 | 0
38 | B.SO1.4.26-06 | Plače mejnih policistov | Projekt | Salaries of border guards | Policija - SGDP | N | 12000000 | -1200000 | 10800000 | 10800000 | 0 |  | 0 | 1450725.31 | 1655746.48 | 1900000 | 1900000 | 1900000 | 1993528.21 | 0
39 | B.SO1.4.26-07 | Plače napotenih policistov na zunanjo schengensko mejo | Projekt | Policija - SGDP | Policija - SGDP | N | 1100000 | 0 | 1100000 | 1100000 | 0 |  | 0 | 0 | 100000 | 250000 | 250000 | 250000 | 250000 | 0
40 | B.SO1.4.26-08 | Vzdrževanje vmesnika za integracijo biometričnih naprav | Projekt | Policija - UIT | Policija - UIT | N | 545700 | 0 | 545700 | 545700 | 0 |  | 0 | 0 | 70000 | 70000 | 105700 | 150000 | 150000 | 0
41 | B.SO1.4.26-09 | Najem poslovnih prostorov za potrebe izvajanja postopkov preverjanja in mejnih postopkov mednarodne zaščite - Pakt (100%) | Projekt | Implementation of EU rules on screening linked to the implementation of the Pact on Migration and Asylum; rental of premises, staff, training (100%) | Policija - UIT | N | 15611248.331 | -11511248.331 | 4100000 | 4100000 | 0 |  | 0 | 0 | 0 | 500000 | 1200000 | 1200000 | 1200000 | 0 |  | 500000 |  | 0
42 | B.SO1.4.26-10 | Financiranje stroškov dela ter izvedbe usposabljanj - Pakt (100%) | Projekt | Implementation of EU rules on screening linked to the implementation of the Pact on Migration and Asylum; rental of premises, staff, training (100%) | Policija - UIT | N | 15611248.331 | -760655.421 | 14850592.91 | 14850592.91 | 0 |  | 0 | 0 | 0 | 3900000 | 3900000 | 3900000 | 3150592.91 | 0 |  | 3900000 |  | 0
| B.SO1.4.27 | Operativna podpora - obsežni informacijski sistemi za namene upravljanja meja | Ukrep |  |  |  | #REF! | #REF! | 535000 | 535000 | 0 | 0 | 0 | 0 | 100000 | 100000 | 335000 | 0 | 0 | 0
43 | B.SO1.4.27-02 | Razvoj in nacionalna implementacija EU projektov v sklopu interoperabilnosti (100%)-operativna podpora | Projekt | Development and national implementation of EU interoperability projects (100%)- operational support | Policija - UIT | N | 535000 | 0 | 535000 | 535000 | 0 |  | 0 | 0 | 100000 | 100000 | 335000 | 0 | 0 | 0
| B.SO1.6 | ETIAS 85(2) (100%) | Vrsta ukrepa |  |  |  | 1044587.5 | 0 | 1044587.5 | 1044587.5 | 0 | 0 | 0 | 0 | 0 | 247250 | 281537.7 | 262000 | 253799.8 | 0
| B.SO1.6.22 | Obsežni informacijski sistemi - ETIAS - 85(2) | Ukrep |  |  |  | 1044587.5 | 0 | 1044587.5 | 1044587.5 | 0 | 0 | 0 | 0 | 0 | 247250 | 281537.7 | 262000 | 253799.8 | 0
44 | B.SO1.6.22-01 | Vzdrževanje ETIAS aplikacije | Projekt | Maintenance of the ETIAS application | Policija - UIT | N | 252787.5 | 0 | 252787.5 | 252787.5 | 0 |  | 0 | 0 | 0 | 47250 | 81537.7 | 62000 | 61999.8 | 0
45 | B.S01.6.22-02 | ETIAS - projektne zaposlitve (plače operaterjev) | Projekt |  | Policija - UKP | N | 791800 | 0 | 791800 | 791800 | 0 |  | 0 | 0 | 0 | 200000 | 200000 | 200000 | 191800 | 0
| B.SO2 | Skupna vizumska politika | Posebni cilj |  |  |  | #REF! | #REF! | 22466666.69 | 18225000 | 4241666.69 | 0 | 835588.0037 | 1900476.8686 | 3155412 | 3669747.34 | 4301224.86 | 4025000 | 4579217.62 | -0.0023
| B.SO2.1 | Ukrepi, zajeti s členom 12(1) (75%) | Vrsta ukrepa |  |  |  | 10275000 | 2450000 | 16966666.69 | 12725000 | 4241666.69 | 0 | 464825.5637 | 1147190.8886 | 2203000 | 2716333.34 | 3201224.86 | 2925000 | 4309092.04 | -0.0023
| B.SO2.1.1 | Izboljšanje obravnave vlog za izdajo vizuma | Ukrep |  |  |  | 840000 | 450000 | 1720000 | 1290000 | 430000 | 0 | 44343.9137 | 64265.2486 | 187000 | 351000 | 435000 | 405000 | 233390.84 | -0.0023
46 | B.SO2.1.1-01 | Standardno konzularno usposabljanje | Projekt |  | MZEZ | N | 330000 | 0 | 440000 | 330000 | 110000 |  | 44343.9137 | 64265.2486 | 87000 | 76000 | 80000 | 80000 | 8390.84 | -0.0023
47 | B.SO2.1.1-02 | Aktivnosti v podporo digitalizaciji obravnave vlog za izdajo vizumov | Projekt |  | MZEZ | N | 510000 | 225000 | 980000 | 735000 | 245000 |  | 0 | 0 | 100000 | 200000 | 280000 | 250000 | 150000 | 0
48 | B.SO2.1.1-03 | Sodelovanje strokovnjakov pri nadzoru schengenskega poslovanja in na sestankih delovnih teles EU (75%) | Projekt | Participation of experts in Schengen monitoring and in meetings of EU working bodies (75%) | MZEZ | N | 225000 | 0 | 300000 | 225000 | 75000 |  | 0 | 0 | 0 | 75000 | 75000 | 75000 | 75000 | 0
| B.SO2.1.2 | Izboljšanje učinkovitosti, strankam prijaznega okolja in varnosti na konzulatih | Ukrep |  |  |  | 1500000 | 0 | 2000000 | 1500000 | 500000 | 0 | 0 | 53203.43 | 177000 | 107000 | 662796.57 | 500000 | 500000 | 0
49 | B.SO2.1.2-01 | Izboljšanje standardov, funkcij in procesov na konzulatih | Projekt |  | MZEZ | N | 1500000 | 0 | 2000000 | 1500000 | 500000 |  | 0 | 53203.43 | 177000 | 107000 | 662796.57 | 500000 | 500000 | 0
| B.SO2.1.3 | Varnost dokumentov/ svetovalci za dokumente | Ukrep |  |  |  | 481750.005 | -0.005 | 642333.34 | 481750 | 160583.34 | 0 | 0 | 0 | 43000 | 64000 | 200000 | 200000 | 135333.34 | 0
50 | B.SO2.1.3-01 | Nakup storitve preverjanja dokumentacije | Projekt |  | MZEZ | N | 481750.005 | -0.005 | 642333.34 | 481750 | 160583.34 |  | 0 | 0 | 43000 | 64000 | 200000 | 200000 | 135333.34 | 0
| B.SO2.1.6 | Obsežni informacijski sistemi - VIS | Ukrep |  |  |  | 3375000 | 2000000 | 7166666.67 | 5375000 | 1791666.67 | 0 | 59825.83 | 496605.22 | 1000000 | 1000000 | 1000000 | 1000000 | 2610235.62 | 0
51 | B.SO2.1.6-01 | Nakup in vzdrževanje programskih komponent nacionalnega vizumskega informacijskega sistema | Projekt |  | MZEZ | N | 3375000 | 2000000 | 7166666.67 | 5375000 | 1791666.67 |  | 59825.83 | 496605.22 | 1000000 | 1000000 | 1000000 | 1000000 | 2610235.62 | 0
| B.SO2.1.7 | Drugi sistemi IKT za namene obravnave vlog za izdajo vizuma | Ukrep |  |  |  | 4078249.995 | 0.005 | 5437666.68 | 4078250 | 1359416.68 | 0 | 360655.82 | 533116.99 | 796000 | 1194333.34 | 903428.29 | 820000 | 830132.24 | 0
52 | B.SO2.1.7-01 | Licence za delovanje programskih komponent nacionalnega vizumskega informacijskega sistema | Projekt |  | MZEZ | N | 865749.9825 | 0.0175 | 1154333.34 | 865750 | 288583.34 |  | 21859.74 | 244631.97 | 162000 | 139000 | 223000 | 180000 | 183841.63 | 0
53 | B.SO2.1.7-02 | Nakup in vzdrževanje IKT strojne opreme | Projekt |  | MZEZ | N | 1500000 | 0 | 2000000 | 1500000 | 500000 |  | 298929.16 | 192642.55 | 370000 | 320000 | 318428.29 | 250000 | 250000 | 0
54 | B.SO2.1.7-03 | Zagotavljanje kvalitetne povezljivosti | Projekt |  | MZEZ | N | 675000 | 0 | 900000 | 675000 | 225000 |  | 39866.92 | 95842.47 | 126000 | 126000 | 126000 | 190000 | 196290.61 | 0
55 | B.SO2.1.7-04 | Pilotni projekt uporabe kioskov za zajemanje biometričnih podatkov | Projekt |  | MZEZ | N | 400000.0125 | -0.0125 | 533333.34 | 400000 | 133333.34 |  | 0 | 0 | 138000 | 395333.34 | 0 | 0 | 0 | 0
56 | B.SO2.1.7-05 | Najem storitve zajema biometričnih podatkov na samopostrežnem pametnem kiosku | Projekt |  | MZEZ | N | 637500 | 0 | 850000 | 637500 | 212500 |  | 0 | 0 | 0 | 214000 | 236000 | 200000 | 200000 | 0
| B.SO2.4 | Operativna podpora (100%) | Vrsta ukrepa |  |  |  | 5500000 | 0 | 5500000 | 5500000 | 0 | 0 | 370762.44 | 753285.98 | 952412 | 953414 | 1100000 | 1100000 | 270125.58 | 0
| B.SO2.4.8 | Operativna podpora - skupna vizumska politika | Ukrep |  |  |  | 5500000 | 0 | 5500000 | 5500000 | 0 | 0 | 370762.44 | 753285.98 | 952412 | 953414 | 1100000 | 1100000 | 270125.58 | 0
57 | B.SO2.4.8-01 | Stroški plač | Projekt |  | MZEZ | N | 5500000 | 0 | 5500000 | 5500000 | 0 |  | 370762.44 | 753285.98 | 952412 | 953414 | 1100000 | 1100000 | 270125.58 | 0
| B.SO3 | Tehnična pomoč | Posebni cilj | [5 empty] | 7069828.0591 | 7069828.0591 | 0 | 0 | 6523.11 | 687519.08 | 1000000 | 1500000 | 3875785.8691 | 0 | 0 | 0
| B.SO3.9 | Tehnična pomoč (100%) | Vrsta ukrepa |  |  |  | 0 |  | 3457575.94 | 3457575.94 | 0 | 0 | 6523.11 | 687519.08 | 724028 | 724028 | 1315477.75 | 0 | 0 | 0
| B.SO3.9.4 | Tehnična pomoč | Ukrep |  |  |  | 0 |  | 3457575.94 | 3457575.94 | 0 | 0 | 6523.11 | 687519.08 | 724028 | 724028 | 1315477.75 | 0 | 0 | 0
58 | B.SO3.9.4-01 | Tehnična pomoč MF - UNP | Projekt |  | MF - UNP | N |  |  | 783127 | 783127 | 0 |  | 0 | 101328 | 174028 | 174028 | 333743
59 | B.SO3.9.4-02 | Tehnična pomoč MF -SUSEU | Projekt |  | MF | N |  |  | 170000 | 170000 | 0 |  | 6523.11 | 12200.73 | 50000 | 50000 | 51276.16
60 | B.SO3.9.4-03 | Tehnična pomoč OU | Projekt |  | MF | N |  |  | 2504448.94 | 2504448.94 | 0 |  | 0 | 573990.35 | 500000 | 500000 | 930458.59
[25 empty] | 1452931.085 | 140173.585
[16 empty] | 15992495.78 | 40419821.84